## Vehicle Dynamics
MEETING DETAILS | Project Name: Simulation of Vehicle Dynamics for Lateral and Longitudinal movement of Vehicle
Team Members: Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav
Date | Task | Name of Convener/Attendee | Status | Remark
21/07/2021 | Presentation for Project Topics | Harshal | Completed
22/07/2021 | Research on project topic | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
24/07/2021 | Topic finalisation | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
26/07/2021 | Call for Collection & study of research papers | Harshal | Completed
27/07/2021 | Research on Stratergy and algorithm of Lateral Motion Control for Autonomous EV | Vaibhav | Completed
27/07/2021 | Simulation Analysis of Vertical and Lateral Dynamics of EV driven by Two rear Hub Motors | Vaibhav | Completed
28/07/2021 | Simulation and Model Verification of a Vehicle Handling Dynamics | Harshal | Completed
28/07/2021 | Longitudinal Vehicle Dynamics using Matlab/Simulink | Dharma | Completed
29/07/2021 | Modelling and Validation of the vehicle longitudinal model | Harshal | Completed
30/07/2021 | Defining the Objectives | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed | Only lateral & longitudnal movement of vehicle tobe taken in consideration
31/07/2021 | Discussion on Vehicle Mechanics and Vehicle Dynamic Blockset | Harshal | Completed
2021-02-08 | Requirements of i/p for simulink model | Sanket | In progress | Creation of trajectory using driving scenario is completed. How to take this block as i/p is remaining
| Defining of o/p for simulink model | Vaibhav | In progress | 2D visualization block implementation
| Study of results, discussion from research papers | Dharma | In progress | Studying the results and Conclusion for research paper
| Gathering referance input forces for vehicle performance | Pooja | Completed | Reference data is gathered for iput following research papers
2021-03-08 | Follow up | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
| Project ppt with requirements submitted | Harshal | Completed
2021-04-08 | Follow up ; Study of VR Visualization | Vaibhav & Sanket | In progress
| Study of results, discussion from research papers | Rahul & Dharma | In progress
| Gathering referance input parameter as a standard from a case study | Pooja | In progress
2021-06-08 | Study of bicycle dynamics; Collection of research papers | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
2021-08-08 | Study of State space representation for an example | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | In progress
2021-09-08 | Collection of reference papers on bicyle dynamics | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
2021-10-08 | Assignment on bicycle breaking | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
2021-11-08 | Formulation of parameters to be considered in model | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed | Forces & parameters finalised in discussion with Rohan sir
2021-11-08 | Wheel angle & tilt angle consideration | Dharma, Pooja | Completed
2021-11-08 | Up hill & down hill consideration | Rahul, Vaibhav | Completed
2021-12-08 | Remodelling of assignment on braking | Sanket & Vaibhav | In progress
13/08/2021 | Remodelling of assignment on braking | Sanket & Vaibhav | Completed
15/08/2021 | A test case of requirements for bicycle model | Pooja | In progress
16/08/2021 | Defining range, data type for specification of parameters | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
17/08/2021 | A test case of requirements for bicycle model | Pooja | Completed
| Utilsation of test case parameters to model using VD blockset | Harshal | Completed
| Remodelling using different parameters | Vaibhav & Sanket | Completed
| Study of results, discussion from research papers | Rahul & Dharma | Completed
18/08/2021 | Group discussion on Error Evaluation | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
20/08/2021 | Vehicle modelling using state space | Harshal | Completed
21/08/2021 | Implementation of required parameters in simulink | Dharma, Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed | i/p and o/p mismatch error
22/08/2021 | Vehicle modelling using simple block and 3DOF Single Track | Sanket | In progress | Braking force to be impelemented
23/08/2021 | Remodelling vehicle modelling using simple block and 3DOF Single Track | Sanket | In progress | Inertia need to be consider
24/08/2021 | Bicycle modelling using simscape & dynamic blockset | Harshal | In progress
25/08/2021 | Demo of model | Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed
| Model implemented with simple block and 3DOF Single Track | Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed | UP/DOWN hill, braking, tilting
| Model implemented with simscape & dynamic blockset | Harshal, Pooja, Rahul, Sanket, Vaibhav | Completed | UP/DOWN hill, braking, tilting, inertia

## Requirements of VD
Parameters to be considered | Parameters to be observed
Padelling force + Torque | Roll
Weight
Frictional force | Yaw
Wheel angle +Tilt angle
Braking force | Velocity
Road(UP hill or DOWN hill)
Parameters to be considered | Nomenclature | Parameters to be observed
Padelling force (Fp)=Driver i/p | R- Radius of front Sprocket | Roll w.r.t. time
Padelling torque (Ƭ)=R*Fp | g- accn due to gravity
Weight (W)=m*g | m- mass of bicycle + mass of driver | Yaw w.r.t. time
Frictional force (Ff)=m*g*µ | μ- Coefficient of friction
Wheel angle (Ψ) = Driver i/p | θ- angle made by bicycle w.r.t road
Tilt angle (Ɵ)= tan^-1[(v^2)/r*g] | v- velocity of bicycle | Velocity w.r.t. time
Braking force = Driver i/p | r- Radius of curvature
Up hill force (P)= m*g*sinα | ∝- angle inclination of road
Down hill force (D)= -m*g*sinα | Ø- angle of friction
Parameter | Unit | Range | Data type | Resolution
Input
mass of bicycle & rider | kg | 0-200kg | uint8 | 1
padelling force | N | 0-1000N | uint16 | 1
UP/DOWN hill angle | degree | 0-45 | uint8 | 1
radius of sprocket wheel | mm | 0-250 | uint8 | 1
braking force | N | 0-1500 | uint16 | 1
handle angle | degree | 0-80 | uint8 | 1
Output
Roll | rad | 0-2 | float | 0.01
Yaw | rad | 0-2 | float | 0.01
Velocity | m/s | 0-20 | float | 0.001
VEHICLE PARAMETERS
Mass of (Rider+ Vehicle) | kg | 1400 | uint8
CG Height | m | 0.95 | uint8
CG Front Axle | m | 0.95 | uint8
CG Rear Axle | m | 0.95 | uint8
Frontal Area | m^2 | 1.33 | uint16
Steering Angle | radians | 30 | uint8
Inertia | kg*m^2 | 1263.5 | uint8
Spring Stiffness Front | N/m | 18000 | uint8
Spring Stiffness Rear | N/m | 1500 | uint8
Tire Parameters Coefficients
tire_b |  | 10 | uint8
tire_c |  | 1.9 | uint8
tire_d |  | 1 | uint8
tire_e |  | 0.97 | uint8
tire_dia | cm | 45.72 | uint8
tire_inertia | kg*m^2 | 0.001 | float
Rolling Resistance |  | 0.005 | float
Tire Stiffness | N/m | 200000 | uint8
Roll | rad | 0-2 | float | 0.01
Yaw | rad | 0-2 | float | 0.01
Velocity | m/s | 0-20 | float | 0.001